## Sheet1
Milestone 1
Task | responsible | Start (in days) | Duration (in days) | End (in days)
Business idea | Farah Khan | 1 | 1 | 2
Gantt chart | Farah Khan | 2 | 1 | 3
UI/UX Design | Khulud Almutairi | 2 | 3 | 5
UI/UX Design | Lian Almutairi | 2 | 3 | 5
GitHub setup | Nouf Albalawi | 4 | 1 | 5
README | Nouf Albalawi | 4 | 1 | 5
Milestone 1 Submission | team | 6 | 1 | 7
Our project was planned and completed within one week. Some of these tasks were performed in parallel to ensure productivity and efficiency, within a manageable time and erly completion of the first milestone of the project.